## Plan
Change Request: XXX ZLSDIXXX - Inbound Interface Pre-Calc from Web E-Ordering | [11 empty] | Start Date
Finishe Date
No. | Work Details | Duration (Days) | Plan Start | Plan Finish | Actual Start | Actual Finish | Responsible |  |  |  |  | Total | 2023-02-01 |  |  | 2023-03-01 | [30 empty] | 2023-04-01 | [29 empty] | 2023-05-01
[7 empty] | ATOS | METRO | TOA Trade | TOA DT-SAP SD | TOA DT - Web |  | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | Get Requirement and Confirm Requirement' | 0.5 | 2023-04-03 | 2023-04-03 |  |  | X | X | X | X | X | bar: 2023-04-01 3
2 | SAP Development | 11 | 2023-04-04 | 2023-04-21 |  |  | X | bar: 2023-04-01 4 to 2023-04-01 7; 2023-04-01 10 to 2023-04-01 12; 2023-04-01 18 to 2023-04-01 21
3 | SAP Unit Testing | 5 | 2023-04-24 | 2023-04-27 |  |  | X | bar: 2023-04-01 24 to 2023-04-01 28
4 | SAP Testing by IT-SD | 3 | 2023-04-28 | 2023-05-03 | [5 empty] | X | bar: 2023-05-01 2 to 2023-05-01 3
5 | Web Development | ?? | ???? | ?? |  |  |  | X
6 | Web Unit Testing | ?? | ?? | ?? |  |  |  | X
7 | Web Testing by IT-Web | ?? | ?? | ?? | [6 empty] | X
8 | Web UAT | ?? | ?? | ?? |  |  |  |  | X | X | X
9 | Deploy & Testing on Live Environment | ?? | ?? | ?? |  |  | X | X |  | X | X
10 | Go-Live | ?? | ?? | ?? |  |  | X | X | X | X | X
DAY(s)
?? - ฝากทีมเว็บ ช่วยหยอดตัวเลขประมาณการให้ด้วยค่ะ

## Action Plan
No. | Plan date | Due Date | Status | Start Date | Finish Date | Activity | Participant | Department/Division | Venue | Remark
1 | 2023-03-02 | - | Completed | 2023-03-02 | 2023-03-02 | Confirm Final Requirement |  | Trade, DT ทีมเว็บ, DT ทีม SAP, Metro | -
2 | 2023-03-09 | 2023-03-09 | Pending | 2023-03-03 |  | Create Change Request | K.Jesada / Trade | Trade | -
3 | 2023-03-09 | 2023-03-09 | Pending | 2023-03-03 |  | Draft Plan ส่วนของเว็บ | K.Pongamorn | DT ทีม เว็บ
4 | [5 empty] | Estimate Actual SAP Mandays |  | ATOS |  | รอ No. 2
5 | 2023-03-20 | 2023-03-20 | Pending | 2023-03-03 |  | Prepare CAB Meeting Slide | K.Jesada / Trade | Trade
6 | 2023-03-24 |  |  |  |  | CAB Meeting | K.Jesada / Trade | Trade, DT ทีมเว็บ, DT ทีม SAP |  | รอ No. 2, 3 , 4
7 | [5 empty] | Create PR -> Approve PR | K.Jesada / Trade | Trade
8 | [5 empty] | Create PO -> Approve PO |  | จัดซื้อ
9 | [5 empty] | Project Kick off |  | Trade, DT ทีมเว็บ, DT ทีม SAP, Metro , ATOS

## Test
1

## Member
Team member | Name | Email address | Department/Company
Project Leader | Jetsada Sukkasem | jetsada_s@toagroup.com | Retail Sales / TOA
Project Leader | Pakawadee Visudthimark | pakawadee@toagroup.com | Retail Sales / TOA
ทีม Web Development | Pongamorn Rodsed | pongamorn_s@toagroup.com | Digital Transformation / TOA
ทีม Web Development | Kasipat Shotikonvorakun | kasipsho@metrosystems.co.th | Metro Systems Corporation PLC.
ทีม Web Development | Phattarapong Poungmalee | phattpou@metrosystems.co.th | Metro Systems Corporation PLC.
ทีม SAP | Chutima Fookaew | chutima_f@toagroup.com | Digital Transformation / TOA
ทีม SAP | Monrudee Jiankraingkai | monrudee@toagroup.com | Digital Transformation / TOA
ทีม SAP | Patoorat Vorakulamornrat | patoorat_v@toagroup.com | Digital Transformation / TOA
ทีม SAP | Ornanong Burirak | ornanong@toagroup.com | Digital Transformation / TOA
ทีม SAP | Kanokwan Phanthuyee | kanokwan_ph@toagroup.com | Digital Transformation / TOA
ทีม ABAP | Adinan Pholchan | adinan@toagroup.com | Digital Transformation / TOA
ทีม BASIS | Chaiwat Chanavirat | chaiwat@toagroup.com | Digital Transformation / TOA
ทีม SAP | Borwon Khammeerak | borwon.khammeerak@atos.net | Atos consulting
ทีม SAP | Wuthichai Limthongbai | wuthichail@atos.net | Atos consulting

## Participant
Team member / Role | Name | Email address | Department/Company | Get Requirement | Development | Unit Testing | UAT
Project Leader | Jetsada Sukkasem | jetsada_s@toagroup.com | Retail Sales / TOA | X |  |  | X
Project Leader | Pakawadee Visudthimark | pakawadee@toagroup.com | Retail Sales / TOA
ทีม Web Development | Pongamorn Rodsed | pongamorn_s@toagroup.com | Digital Transformation / TOA | X | X | X
ทีม Web Development | Kasipat Shotikonvorakun | kasipsho@metrosystems.co.th | Metro Systems Corporation PLC. | X | X | X
ทีม Web Development | Phattarapong Poungmalee | phattpou@metrosystems.co.th | Metro Systems Corporation PLC. | X | X | X
ทีม SAP | Chutima Fookaew | chutima_f@toagroup.com | Digital Transformation / TOA | X | X | X
ทีม SAP | Monrudee Jiankraingkai | monrudee@toagroup.com | Digital Transformation / TOA | X | X | X
ทีม SAP | Patoorat Vorakulamornrat | patoorat_v@toagroup.com | Digital Transformation / TOA | X | X | X
ทีม SAP | Ornanong Burirak | ornanong@toagroup.com | Digital Transformation / TOA | X | X | X
ทีม SAP | Kanokwan Phanthuyee | kanokwan_ph@toagroup.com | Digital Transformation / TOA
ทีม ABAP | Adinan Pholchan | adinan@toagroup.com | Digital Transformation / TOA
ทีม BASIS | Chaiwat Chanavirat | chaiwat@toagroup.com | Digital Transformation / TOA
ทีม SAP | Borwon Khammeerak | borwon.khammeerak@atos.net | Atos consulting | X
ทีม SAP | Wuthichai Limthongbai | wuthichail@atos.net | Atos consulting | X

## Notes
No. | Description
1 | ????
2 | ????
3 | ????